## Sheet1
sprint# | group# | group task description | task# | task description | deviations (from original plan) | status | remarks
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB001 | Create FastAPI project skeleton with basic app factory and routing structure. |  | pending
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB002 | Implement configuration loader (env-based) for DB paths, Kite keys, and app settings. |  | pending
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB003 | Design and create sigmaqlab_meta.db schema migration for core tables (strategies, strategy_parameters, backtests). |  | pending
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB004 | Set up structured logging for backend (JSON or key-value format) with log levels and request logging. |  | pending
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF001 | Create React + TypeScript + Vite (or CRA) app and integrate Material UI. |  | pending
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF002 | Implement global layout: AppBar with SigmaQLab branding, navigation skeleton, and basic dark theme. |  | pending
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF003 | Set up React Router with routes for Dashboard, Strategies, Backtests, Data, Settings. |  | pending
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TB001 | Configure backend tooling: black, isort, mypy/ruff, and add pre-commit hooks. |  | pending
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TF002 | Configure frontend tooling: ESLint, Prettier, TypeScript strict settings. |  | pending
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TB003 | Add basic test harness for backend (pytest) with one sample test to validate CI wiring. |  | pending
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB001 | Implement Zerodha Kite client wrapper for historical OHLCV and holdings (read-only). |  | pending
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB002 | Implement optional yfinance/CSV loader as fallback data provider. |  | pending
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB003 | Design and create sigmaqlab_prices.db schema (price_bars table with indices). |  | pending
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB004 | Implement Data Service functions to fetch, normalize, and persist OHLCV data from providers into price DB. |  | pending
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB005 | Expose FastAPI endpoint to trigger data fetch for given symbol, timeframe, and date range. |  | pending
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF001 | Create Data page with form to trigger data fetch via API (symbol, timeframe, date range). |  | pending
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF002 | Implement table listing available symbol/timeframe combinations and coverage ranges. |  | pending
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF003 | Add simple price & volume preview chart for selected symbol/timeframe using chosen charting library. |  | pending
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB001 | Implement Strategy CRUD endpoints (create, list, get, update, delete) in FastAPI. |  | pending
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB002 | Implement Strategy Parameters CRUD endpoints and tie them to strategies. |  | pending
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB003 | Add fields for tags, categories, statuses, and integration metadata in schema and API models. |  | pending
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF001 | Implement Strategies list view with filters (status, category, search) and pagination. |  | pending
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF002 | Implement Strategy detail view showing description, tags, and recent backtests placeholder. |  | pending
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF003 | Add parameter set management UI (list, create, edit, delete) for each strategy. |  | pending
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB001 | Define Strategy Engine interface and BacktestResult data models in backend. |  | pending
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB002 | Integrate Backtrader as primary engine and implement adapter that conforms to engine interface. |  | pending
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB003 | Implement one reference strategy in Backtrader (e.g., simple SMA crossover) wired to a Strategy record. |  | pending
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TB001 | Implement API to run a single backtest given strategy_id, params_id, symbols, timeframe, and date range. |  | pending
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TF002 | Add 'Run Backtest' modal/dialog in Strategy detail view to configure and submit a backtest. |  | pending
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TF003 | Create basic Backtests list page showing submitted runs, status, and key summary fields. |  | pending
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB001 | Persist equity curve and trades from Backtrader runs into backtest_equity_points and backtest_trades tables. |  | pending
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB002 | Compute key metrics (total return, max drawdown, win rate, average win/loss, trade count) and store in metrics_json. |  | pending
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB003 | Expose API endpoints to fetch backtest summary, equity series, and trades for a given backtest_id. |  | pending
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF001 | Implement Backtest detail page with summary metrics and equity curve chart (interactive). |  | pending
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF002 | Add trades table with sorting/filtering, showing entry/exit, P&L, and basic stats. |  | pending
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF003 | Optionally overlay buy/sell markers on price chart for one-symbol backtests. |  | pending
S06 | G01 | Batch backtesting: grid search and parallel execution | S06_G01_TB001 | Extend backtest API to accept parameter grids or multiple parameter sets for batch execution. |  | pending
S06 | G01 | Batch backtesting: grid search and parallel execution | S06_G01_TB002 | Implement batch execution using ProcessPoolExecutor with isolation per run. |  | pending
S06 | G01 | Batch backtesting: grid search and parallel execution | S06_G01_TB003 | Store batch group identifier to link multiple backtests that belong to one optimization run. |  | pending
S06 | G02 | Optimization UI: batch backtests and parameter-performance views | S06_G02_TF001 | Create UI to configure and submit batch backtests (parameter ranges, symbol universe). |  | pending
S06 | G02 | Optimization UI: batch backtests and parameter-performance views | S06_G02_TF002 | Implement batch results view showing parameter combinations and key metrics in tabular form. |  | pending
S06 | G02 | Optimization UI: batch backtests and parameter-performance views | S06_G02_TF003 | Add simple visualization (e.g., heatmap or scatter plot) of parameters vs performance. |  | pending
S07 | G01 | Portfolio snapshots: schema, API, and import from Kite | S07_G01_TB001 | Create portfolio_snapshots schema and CRUD endpoints for storing holdings snapshots. |  | pending
S07 | G01 | Portfolio snapshots: schema, API, and import from Kite | S07_G01_TB002 | Implement Data Service function to import current holdings from Kite into a portfolio snapshot. |  | pending
S07 | G01 | Portfolio snapshots: schema, API, and import from Kite | S07_G01_TF003 | Add Portfolio page UI to list snapshots and show holdings with core/tactical tagging controls. |  | pending
S07 | G02 | Portfolio-aware backtests: starting portfolio and constraints | S07_G02_TB001 | Extend backtest engine config to accept a starting portfolio snapshot and core/tactical constraints. |  | pending
S07 | G02 | Portfolio-aware backtests: starting portfolio and constraints | S07_G02_TB002 | Update metrics to report portfolio-level impact (realized + unrealized changes vs baseline). |  | pending
S07 | G02 | Portfolio-aware backtests: starting portfolio and constraints | S07_G02_TF003 | Update Backtest configuration UI to allow selecting a portfolio snapshot when running a backtest. |  | pending
S07 | G03 | Integration hooks: expose strategy summaries for SigmaTrader | S07_G03_TB001 | Implement read-only API endpoint to return latest backtest summary for a given strategy_id for external consumers (SigmaTrader). |  | pending
S07 | G03 | Integration hooks: expose strategy summaries for SigmaTrader | S07_G03_TB002 | Ensure strategies can store and display linked SigmaTrader IDs and TradingView templates in the UI. |  | pending