## Sheet1
sprint# | group# | group task description | task# | task description | remarks | status | deviations (from original plan)
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB001 | Create FastAPI project skeleton with basic app factory and routing structure. | FastAPI app factory and /health endpoint created. | implemented
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB002 | Implement configuration loader (env-based) for DB paths, Kite keys, and app settings. | Env-based Settings config using pydantic-settings added. | implemented
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB003 | Design and create sigmaqlab_meta.db schema migration for core tables (strategies, strategy_parameters, backtests). | sigmaqlab_meta.db schema for strategies/params/backtests wired via SQLAlchemy. | implemented
S01 | G01 | Backend foundation: FastAPI skeleton, config, meta DB setup | S01_G01_TB004 | Set up structured logging for backend (JSON or key-value format) with log levels and request logging. | JSON logging with level/timestamp and Uvicorn integration configured. | implemented
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF001 | Create React + TypeScript + Vite (or CRA) app and integrate Material UI. | React + TS + Vite + MUI frontend scaffolded. | implemented
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF002 | Implement global layout: AppBar with SigmaQLab branding, navigation skeleton, and basic dark theme. | Global dark theme and SigmaQLab layout (AppBar + nav) implemented. | implemented
S01 | G02 | Frontend foundation: React+TS+MUI scaffold and base layout | S01_G02_TF003 | Set up React Router with routes for Dashboard, Strategies, Backtests, Data, Settings. | React Router routes for Dashboard/Strategies/Backtests/Data/Settings added. | implemented
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TB001 | Configure backend tooling: black, isort, mypy/ruff, and add pre-commit hooks. | Backend tooling (black, ruff, pytest, pre-commit) configured. | implemented
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TF002 | Configure frontend tooling: ESLint, Prettier, TypeScript strict settings. | Frontend tooling (ESLint, Prettier, strict TS) configured. | implemented
S01 | G03 | Developer experience: tooling, linting, and pre-commit | S01_G03_TB003 | Add basic test harness for backend (pytest) with one sample test to validate CI wiring. | Basic pytest harness with /health test in place. | implemented
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB001 | Implement Zerodha Kite client wrapper for historical OHLCV and holdings (read-only). | Kite client wrapper for historical OHLCV implemented. | implemented
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB002 | Implement optional yfinance/CSV loader as fallback data provider. | yfinance and CSV data providers added as fallbacks. | implemented
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB003 | Design and create sigmaqlab_prices.db schema (price_bars table with indices). | sigmaqlab_prices.db and price_bars schema created. | implemented
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB004 | Implement Data Service functions to fetch, normalize, and persist OHLCV data from providers into price DB. | DataService to fetch/normalise/persist OHLCV into prices DB implemented. | implemented
S02 | G01 | Data service: Kite/yfinance integration and price DB persistence | S02_G01_TB005 | Expose FastAPI endpoint to trigger data fetch for given symbol, timeframe, and date range. | /api/data/fetch endpoint added and covered by tests. | implemented
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF001 | Create Data page with form to trigger data fetch via API (symbol, timeframe, date range). | Data page fetch form wired to backend data fetch API. | implemented
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF002 | Implement table listing available symbol/timeframe combinations and coverage ranges. | Coverage summary table with source column, row selection, Select All, and Delete Selected controls. | implemented
S02 | G02 | Data management UI: fetch, list, and preview data | S02_G02_TF003 | Add simple price & volume preview chart for selected symbol/timeframe using chosen charting library. | Preview now uses lightweight-charts with grouped indicator toggles, tall adjustable chart, volume bars toggle, range presets (intraday + calendar), simple tools (last price line/latest-bar marker), and synced price/oscillator panes. | implemented
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB001 | Implement Strategy CRUD endpoints (create, list, get, update, delete) in FastAPI. | Strategy CRUD API endpoints implemented. | implemented
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB002 | Implement Strategy Parameters CRUD endpoints and tie them to strategies. | Strategy parameter CRUD endpoints wired to strategies. | implemented
S03 | G01 | Strategy service: metadata and parameter storage | S03_G01_TB003 | Add fields for tags, categories, statuses, and integration metadata in schema and API models. | Tags/category/status/integration fields exposed in API models. Engine code field added to Strategy schema and API models so multiple business codes can share one engine implementation. | implemented
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF001 | Implement Strategies list view with filters (status, category, search) and pagination. | Strategy list view in React (table) with edit/delete implemented. Strategies list shows engine implementation and supports filtering by engine_code. | implemented
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF002 | Implement Strategy detail view showing description, tags, and recent backtests placeholder. | Strategy detail panel with status/tags/integration fields added. | implemented
S03 | G02 | Strategy Library UI: list, details, and parameter sets | S03_G02_TF003 | Add parameter set management UI (list, create, edit, delete) for each strategy. | Parameter sets table and JSON-based create/edit/delete wired to API. | implemented
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB001 | Define Strategy Engine interface and BacktestResult data models in backend. | BacktestConfig/BacktestResult engine interface and types defined. Backtest engine registry now keyed by engine_code (e.g. SmaCrossStrategy) with aliases for SMA_X* codes. | implemented
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB002 | Integrate Backtrader as primary engine and implement adapter that conforms to engine interface. | Backtrader engine (SMA_X) integrated behind StrategyEngine interface. | implemented
S04 | G01 | Backtest engine: Backtrader integration and engine interface | S04_G01_TB003 | Implement one reference strategy in Backtrader (e.g., simple SMA crossover) wired to a Strategy record. | BacktestService runs engine using DB price_bars and persists Backtest rows. BacktestService now uses Strategy.engine_code (falling back to code) when selecting engine implementation. | implemented
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TB001 | Implement API to run a single backtest given strategy_id, params_id, symbols, timeframe, and date range. | POST /api/backtests endpoint wired to BacktestService and covered by tests. | implemented
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TF002 | Add 'Run Backtest' modal/dialog in Strategy detail view to configure and submit a backtest. | Run backtest configuration form implemented on Backtests page instead of a modal in Strategy details. | implemented | UI deviation: backtest configuration lives on /backtests page; a strategy-scoped modal can be added later if needed.
S04 | G02 | Backtest execution: API endpoint and simple UI trigger | S04_G02_TF003 | Create basic Backtests list page showing submitted runs, status, and key summary fields. | Backtests page lists recent runs with strategy, symbol, timeframe, status, PnL, and final value. | implemented
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB001 | Persist equity curve and trades from Backtrader runs into backtest_equity_points and backtest_trades tables. | backtest_equity_points and backtest_trades tables added; engine now returns equity_curve and trades which are persisted per backtest. | implemented
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB002 | Compute key metrics (total return, max drawdown, win rate, average win/loss, trade count) and store in metrics_json. | BacktestService computes total_return, max_drawdown, trade_count, win_rate, avg_win, avg_loss and stores them in metrics_json. | implemented
S05 | G01 | Backtest results: persistence and metrics calculation | S05_G01_TB003 | Expose API endpoints to fetch backtest summary, equity series, and trades for a given backtest_id. | API exposes /api/backtests/{id}/equity and /api/backtests/{id}/trades for detailed results. | implemented
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF001 | Implement Backtest detail page with summary metrics and equity curve chart (interactive). | Backtests page now shows a Backtest Details panel with summary metrics and an equity curve chart for the selected run. | implemented
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF002 | Add trades table with sorting/filtering, showing entry/exit, P&L, and basic stats. | Trades table added to Backtest Details panel, listing entry/exit, side, size, and PnL for each trade. | implemented
S05 | G02 | Backtest detail UI: equity chart, trades table, and parameters | S05_G02_TF003 | Optionally overlay buy/sell markers on price chart for one-symbol backtests. | Backtest Details panel also shows the parameter set used (when available), with JSON rendered readably. | implemented
S06 | G01 | Backtest Overhaul: backend metrics and projections | S06_G01_TB001 | Extend Backtest model to store effective params, risk/cost/visualization configs, and richer metrics_json. | Backtest model extended with label/notes and JSON configs (params_effective/risk/costs/visual), plus migration helper. | implemented
S06 | G01 | Backtest Overhaul: backend metrics and projections | S06_G01_TB002 | Introduce backtest_trades and backtest_equity_points persistence (or equivalent) for trades and equity curves. | backtest_trades/backtest_equity_points persisted with extra per-trade metrics (pnl_pct, holding_period_bars, max_theoretical_pnl, capture ratio). | implemented
S06 | G01 | Backtest Overhaul: backend metrics and projections | S06_G01_TB003 | Compute expanded backtest metrics (Sharpe, Sortino, alpha/beta, Calmar, volatility) from equity series. | Equity-based metrics (total_return, max_drawdown, volatility, Sharpe, Sortino, annual_return, Calmar) computed in BacktestService. | implemented
S06 | G01 | Backtest Overhaul: backend metrics and projections | S06_G01_TB004 | Implement unrealised projection and per-trade what-if metrics using trades and price series. | Per-trade what-if metrics derived from price series and stored on BacktestTrade (what-if/max PnL and capture ratios). | implemented
S06 | G02 | Backtest Overhaul: chart and series APIs | S06_G02_TB001 | Add /api/backtests/{id}/chart-data endpoint returning price_bars, indicators, equity, projection, and trade markers. | Added /api/backtests/{id}/chart-data returning price_bars, indicators, equity, projection, and trades (BacktestChartDataResponse). | implemented
S06 | G02 | Backtest Overhaul: chart and series APIs | S06_G02_TB002 | Add /api/backtests/{id}/trades endpoint returning enriched trade records with what-if metrics. | Enriched BacktestTradeRead and /api/backtests/{id}/trades with per-trade metrics (pnl_pct, holding_period_bars, max_theoretical_pnl, capture ratio). | implemented
S06 | G02 | Backtest Overhaul: chart and series APIs | S06_G02_TB003 | Add /api/backtests/{id}/trades/export?format=csv endpoint for backend-generated CSV exports. | Implemented /api/backtests/{id}/trades/export CSV endpoint for downloading backtest trades. | implemented
S06 | G02 | Backtest Overhaul: chart and series APIs | S06_G02_TB004 | Expose expanded metrics via backtest detail API (either enriched /api/backtests/{id} or dedicated metrics endpoint). | Metrics exposed via BacktestRead (GET /api/backtests/{id}) and reused inside chart-data backtest field. | implemented
S07 | G01 | Backtest Overhaul UI: backtest detail chart (price, volume, indicators, trades) | S07_G01_TF001 | Create Backtest detail view route/page that loads /api/backtests/{id}/chart-data and renders lightweight-charts price + volume + RSI panes. | Reuse Data preview chart infra where sensible. | pending
S07 | G01 | Backtest Overhaul UI: backtest detail chart (price, volume, indicators, trades) | S07_G01_TF002 | Render buy/sell markers and optional PnL labels on the backtest chart based on trade signals. | Markers and tooltips per qlab_bt_overhaul_prd.md 2.1.2. | pending
S07 | G01 | Backtest Overhaul UI: backtest detail chart (price, volume, indicators, trades) | S07_G01_TF003 | Visualise unrealised projection overlay on the chart and ensure panes stay time-synchronised. | Projection overlay behaviour per qlab_bt_overhaul_prd.md 2.2. | pending
S07 | G02 | Backtest Overhaul UI: strategy/backtest settings panel | S07_G02_TF001 | Implement settings panel (modal or drawer) with tabs for Inputs, Risk, Costs, Visualization, and Meta/Notes. | Overall layout per qlab_bt_overhaul_prd.md 2.3. | pending
S07 | G02 | Backtest Overhaul UI: strategy/backtest settings panel | S07_G02_TF002 | Wire Inputs tab to strategy parameter sets and per-backtest overrides used when calling POST /api/backtests. | Maps params_json to UI controls. | pending
S07 | G02 | Backtest Overhaul UI: strategy/backtest settings panel | S07_G02_TF003 | Wire Risk, Costs, and Visualization tabs to backend config fields so that backtests run with the chosen settings. | Persists risk/costs/visual configs as per qlab_bt_overhaul_prd.md 2.3. | pending
S07 | G03 | Backtest Overhaul UI: trades table and exports | S07_G03_TF001 | Create rich trades table in Backtest detail view with columns for entry/exit, PnL, what-if PnL, and filters/sorting. | Trade columns per qlab_bt_overhaul_prd.md 2.4.1. | pending
S07 | G03 | Backtest Overhaul UI: trades table and exports | S07_G03_TF002 | Hook up Export button to /api/backtests/{id}/trades/export and trigger CSV download from the UI. | Implements UI side of CSV export. | pending
S07 | G03 | Backtest Overhaul UI: trades table and exports | S07_G03_TF003 | Link trade table selection to chart markers and projection segments for interactive inspection. | Selecting a trade highlights corresponding chart region. | pending
S08 | G01 | Backtest Overhaul: documentation, regression tests, and polish | S08_G01_TB001 | Add backend pytest coverage for new metrics, chart-data, trades, and export endpoints, including edge cases. | Focus on regression safety per qlab_bt_overhaul_prd.md 5.1. | pending
S08 | G01 | Backtest Overhaul: documentation, regression tests, and polish | S08_G01_TF002 | Add or update frontend tests for Backtest detail chart, trades table, and settings panel interactions. | Aligns with qlab_bt_overhaul_prd.md 5.2. | pending
S08 | G01 | Backtest Overhaul: documentation, regression tests, and polish | S08_G01_TB003 | Update qlab_impl_report.md and qlab_user_manual.md to document Backtest Overhaul features and workflows. | To be run towards the end of BT Overhaul. | pending